## Table_Catalog
Predictive Overrun Model — Table Catalog
Table | Grain | Primary Key | Rows | Purpose
projects_clean.csv | One row per valid project snapshot | Project_ID | 2,362 | Project attributes and early cost/schedule controls
workflow_features_clean.csv | One row per valid project snapshot | Project_ID | 2,362 | RFI, change, contingency, and workflow features
outcomes_clean.csv | One row per completed project | Project_ID | 2,362 | Final cost and schedule targets
modeling_dataset_clean.csv | One row per complete modeling relationship | Project_ID | 2,362 | Joined predictors, targets, and time split

## Projects
Projects — Field Dictionary
Field | Data Type | Definition | Model Predictor
Project_ID | Text | Unique synthetic project identifier | No
Project_Name | Text | Fictional project name | No
Project_Type | Category | Construction project type | Yes
Region | Category | U.S. geographic region | Yes
State | Category | U.S. state abbreviation | Yes
Client_Type | Category | Private, Public, or P3 client type | Yes
Contract_Type | Category | Commercial contract structure | Yes
Delivery_Method | Category | Design-Bid-Build, Design-Build, CMAR, or IPD | Yes
Complexity_Level | Ordinal category | Low through Very High project complexity | Yes
Digital_Coordination_Level | Ordinal category | Digital coordination maturity | Yes
Owner_Decision_Profile | Ordinal category | Fast, Standard, or Slow decision environment | Yes
Start_Date | Date | Project start date | No
Snapshot_Date | Date | Early/mid-project model snapshot date | No
Snapshot_Year | Integer | Year used for time-based split | No
Original_Budget | Currency | Original authorized project budget | Yes
Planned_Duration_Days | Integer | Original planned duration | Yes
Planned_Percent_Complete | Percent | Planned completion at snapshot | Yes
Actual_Percent_Complete | Percent | Actual completion at snapshot | Yes
CPI_Snapshot | Decimal | Cost Performance Index at snapshot | Yes
SPI_Snapshot | Decimal | Schedule Performance Index at snapshot | Yes
Cost_Variance_Pct_Snapshot | Percent | Cost variance at snapshot | Yes
Schedule_Variance_Days_Snapshot | Integer | Schedule variance days at snapshot | Yes
Labor_Productivity_Index | Decimal | Relative labor productivity at snapshot | Yes
Procurement_Delay_Days_to_Date | Integer | Observed procurement delay days | Yes
Weather_Impact_Days_to_Date | Integer | Observed weather impact days | Yes
Safety_Incident_Rate_to_Date | Decimal | Synthetic safety incident rate to snapshot | Yes
Snapshot_Data_Completeness_Pct | Percent | Data completeness score | Yes

## Workflow_Features
Workflow Features — Field Dictionary
Field | Data Type | Definition | Model Predictor
Project_ID | Text | Foreign key to project snapshot | No
RFI_Count_to_Date | Integer | RFIs recorded by snapshot | Yes
RFI_Count_per_10M | Decimal | RFI count normalized per $10M budget | Yes
Avg_RFI_Response_Days | Decimal | Average RFI response days to snapshot | Yes
RFI_On_Time_Rate | Percent | On-time responded RFIs divided by responded RFIs | Yes
Overdue_RFI_Rate | Percent | Overdue open RFIs divided by RFIs to date | Yes
High_Critical_Overdue_Rate | Percent | High/Critical overdue RFIs divided by RFIs to date | Yes
RFI_Revision_Rate | Percent | RFIs with revisions divided by RFIs to date | Yes
RFI_Reopen_Rate | Percent | Reopened RFIs divided by RFIs to date | Yes
RFI_to_Change_Rate | Percent | RFIs linked to change divided by RFIs to date | Yes
Approved_Change_Value_Pct_Budget | Percent | Approved change value divided by budget | Yes
Pending_Change_Exposure_Pct_Budget | Percent | Pending change exposure divided by budget | Yes
Change_Approval_Cycle_Days | Decimal | Average change approval cycle to snapshot | Yes
Old_Pending_Change_Rate | Percent | Old pending changes divided by pending changes | Yes
Forecast_Incorporation_Lag_Days | Decimal | Approval-to-forecast incorporation lag | Yes
Contingency_Utilization_Pct | Percent | Contingency used divided by original contingency | Yes
Revision_Loop_Rate | Percent | Workflow return loops divided by events | Yes
Workflow_Handoff_Rate | Percent | Role handoffs divided by workflow events | Yes
Workflow_Risk_Score_Snapshot | Integer | Transparent Project 2-inspired workflow score | Yes

## Outcomes
Outcomes — Target Dictionary
Field | Data Type | Definition | Model Role
Project_ID | Text | Foreign key to project | No
Final_Cost_Overrun_Pct | Percent | Final EAC or actual cost growth over original budget | Target magnitude
Final_Schedule_Delay_Days | Integer | Final delay relative to planned duration | Target magnitude
Cost_Overrun_Flag | Binary | 1 when final cost overrun is at least 10% | Classification target
Schedule_Delay_Flag | Binary | 1 when final schedule delay is at least 30 days | Classification target
Combined_Overrun_Flag | Binary | 1 when either classification target is positive | Secondary target
Final_CPI | Decimal | Final cost performance index | Post-outcome reference
Final_SPI | Decimal | Final schedule performance index | Post-outcome reference
Final_Status | Category | Final project status | Post-outcome reference
Actual_End_Date | Date | Synthetic actual end date | Post-outcome reference
Final_EAC | Currency | Synthetic final estimate at completion | Post-outcome reference

## Feature_Lineage
Feature Lineage from Projects 1 and 2
Feature | Source Project | Definition | Modeling Role
CPI_Snapshot | Project 1 | Cost performance index at snapshot | Early cost-efficiency signal
SPI_Snapshot | Project 1 | Schedule performance index at snapshot | Early schedule-efficiency signal
Cost_Variance_Pct_Snapshot | Project 1 | Snapshot cost variance percentage | Current cost deviation
Schedule_Variance_Days_Snapshot | Project 1 | Snapshot schedule variance in days | Current schedule deviation
Contingency_Utilization_Pct | Project 1 | Contingency used divided by original contingency | Cost-risk absorption
Avg_RFI_Response_Days | Project 2 | Average final response days for RFIs to date | Decision-cycle condition
Overdue_RFI_Rate | Project 2 | Overdue open RFIs divided by RFIs to date | Backlog condition
High_Critical_Overdue_Rate | Project 2 | High/Critical overdue RFIs divided by RFIs to date | Critical decision exposure
RFI_Revision_Rate | Project 2 | RFIs with revisions divided by RFIs to date | Workflow quality
RFI_to_Change_Rate | Project 2 | RFIs linked to change divided by RFIs to date | Commercial conversion
Approved_Change_Value_Pct_Budget | Projects 1 and 2 | Approved change value divided by original budget | Approved commercial growth
Pending_Change_Exposure_Pct_Budget | Project 2 | Pending submitted value divided by original budget | Unresolved exposure
Change_Approval_Cycle_Days | Project 2 | Average approved change cycle at snapshot | Decision speed
Old_Pending_Change_Rate | Project 2 | Pending changes older than threshold divided by pending changes | Aging condition
Forecast_Incorporation_Lag_Days | Project 2 | Average days from approval to forecast incorporation | Forecast-control discipline
Revision_Loop_Rate | Project 2 | Workflow returns divided by relevant workflow events | Rework and quality
Workflow_Handoff_Rate | Project 2 | Role handoffs divided by workflow events | Coordination complexity
Workflow_Risk_Score_Snapshot | Project 2 | Transparent snapshot workflow-risk score | Composite operational signal

## Quality_Rules
Data Quality and Modeling Rules
Rule ID | Domain | Rule | Severity
DQ-01 | Project keys | Project_ID unique and nonblank | Critical
DQ-02 | Relationships | Workflow and outcome Project_ID must reference a valid clean project | Critical
DQ-03 | Snapshot dates | Snapshot date must be on or after start date | Critical
DQ-04 | Rates | Rates must remain within defined bounds | Critical
DQ-05 | Predictors | CPI, SPI, labor productivity, and required workflow predictors cannot be missing | Critical
DQ-06 | Target integrity | Classification flags must be recalculated from final outcomes | Critical
DQ-07 | Leakage | Final outcome and post-outcome fields cannot enter predictor matrices | Critical
DQ-08 | Time split | 2025 test set cannot be used for tuning | Critical