## Lists
Status | Priority | Owner | Decision
Not Started | Critical | Executive Sponsor | Accept
In Progress | High | Project Controls Lead | Override
Blocked | Medium | Project Manager | Escalate
Complete | Low | Data Scientist | Defer
Deferred |  | Data Engineer
Model Risk Reviewer

## Monitoring_Thresholds
Model Monitoring Thresholds
Proposed governance limits for a future controlled pilot; not a production authorization.
ID | Metric | Baseline | Yellow Limit | Red Limit | Direction | Frequency | Owner | Required Action | Notes
MON-01 | Cost ROC-AUC | 0.8991 | 0.82 | 0.78 | Higher | Quarterly | Model Risk Reviewer | Review if Yellow; suspend if Red | Outcome labels required
MON-02 | Schedule ROC-AUC | 0.75608 | 0.75 | 0.7 | Higher | Quarterly | Model Risk Reviewer | Review if Yellow; suspend if Red | Temporal degradation already observed
MON-03 | Cost Brier score | 0.12286 | 0.15 | 0.18 | Lower | Monthly | Data Scientist | Recalibrate or retrain | Probability calibration
MON-04 | Schedule Brier score | 0.18311 | 0.18 | 0.22 | Lower | Monthly | Data Scientist | Recalibrate or retrain | Probability calibration
MON-05 | Probability PSI | 0.10545 | 0.1 | 0.2 | Lower | Monthly | Data Scientist | Investigate at Yellow; retrain at Red | Feature/output drift
MON-06 | Critical data-quality pass rate | 100% | 100% | 98% | Higher | Each Refresh | Data Engineer | Stop scoring after any critical failure | Mandatory
MON-07 | Segment ROC-AUC gap | 0 | 0.1 | 0.15 | Lower | Quarterly | Model Risk Reviewer | Investigate affected segments | Minimum 25 projects
MON-08 | Override rate | 0 | 0.3 | 0.5 | Lower | Monthly | Project Controls Lead | Review model or process if excessive | Overrides require reason
MON-09 | Scoring success rate | 1 | 0.99 | 0.95 | Higher | Each Run | Data Engineer | Stop and investigate failures | Batch control
MON-10 | Model age months | 0 | 12 | 18 | Lower | Monthly | Data Scientist | Annual review; mandatory retrain review at 18 months | Version 1.0.0

## Executive_Summary
Predictive Overrun Model — Act and Governance Plan
Controlled-pilot roadmap, human review, monitoring, overrides, retraining, and incident response.
0.8991 |  |  | 0.75608 |  | 0.12286 | 0.18311
Cost ROC-AUC |  |  | Schedule ROC-AUC |  | Cost Brier | Schedule Brier
188 |  |  | 138 |  | 110 | 0.10545
Red Test Projects |  |  | Yellow Test Projects |  | Green Test Projects | Schedule PSI Demo
Control Outcome | Standard | Decision Rule | Accountable Role | Evidence
Governed pilot | No autonomous decisions | Human reviewer accepts, overrides, escalates, or defers | Executive Sponsor | Pilot charter approved
Data control | 100% critical checks pass before scoring | Failed refresh stops scoring and publication | Data Engineer | Validation report
Model review | Monthly drift and calibration; quarterly outcome review | Yellow or Red triggers documented | Model Risk Reviewer | Monitoring report
Project action | Red projects receive documented review | Prediction linked to specific controls actions | Project Controls Lead | Review record
Retraining | Annual review or trigger-based retraining | New version independently validated | Data Scientist | Model release record
Risk Band | Projects
Red | 188
Yellow | 138
Green | 110
Important: This Act plan defines controls for a future governed pilot. It does not authorize production scoring on real construction projects. All existing results are synthetic.

## 30_60_90_Roadmap
30/60/90-Day Controlled-Pilot Roadmap
Sequence from governance preparation to limited pilot, monitoring, and go/no-go decision.
Window | Objective | Activities | Owner | Deliverable | Decision Gate | Dependencies | Success Measure
Days 0–30 | Governance foundation | Approve model purpose, prohibited uses, owners, review form, override reasons, data-quality gates, and pilot scope. | Executive Sponsor | Pilot charter | Independent risk review complete | No real scoring until approval | Signed charter
Days 0–30 | Technical reproducibility | Re-run generation, cleaning, training, scoring, and dashboard refresh from a clean environment. | Data Scientist | Reproducibility report | All hashes and metrics reconciled | Controlled environment | Passed rerun
Days 0–30 | Data mapping | Map real source fields to model features without loading client data into the portfolio repository. | Data Engineer | Data mapping specification | Critical fields available and governed | Source-system access | Approved mapping
Days 31–60 | Silent pilot | Score a limited approved portfolio without showing predictions to decision-makers; compare data completeness and distributions. | Data Scientist | Silent-pilot report | No critical quality or drift failure | Approved de-identified data | Monitoring within limits
Days 31–60 | Human-review training | Train reviewers on probability, risk bands, limitations, overrides, and required evidence. | Project Controls Lead | Reviewer certification | Reviewers pass scenario exercise | Training availability | 100% reviewers trained
Days 31–60 | Threshold review | Evaluate validation thresholds against pilot prevalence and management capacity. | Model Risk Reviewer | Threshold memo | Thresholds approved or revised without test leakage | Outcome lag acknowledged | Decision documented
Days 61–90 | Limited visible pilot | Show scores to a small reviewer group; record decisions, overrides, reasons, and actions. | Project Controls Lead | Pilot review log | No prohibited use or unresolved incident | Silent pilot passed | Review completion ≥95%
Days 61–90 | Monitoring review | Evaluate drift, calibration, segment performance, data quality, override rate, and action completion. | Model Risk Reviewer | Monitoring decision | Continue, recalibrate, retrain, or stop | Sufficient labels | Decision signed
Days 61–90 | Go/no-go decision | Executive committee decides whether to continue controlled pilot, redesign, or stop. | Executive Sponsor | Go/no-go record | All conditions explicitly accepted | Independent review | Formal decision

## Model_Governance
Model Governance and Decision Rights
Every score requires an accountable human decision and documented evidence.
Role | Default Owner | Responsibilities | Authority / Limitation | Evidence
Model owner | Data Scientist | Maintain code, models, manifest, and model card | Cannot authorize project action alone | Model release record
Business owner | Project Controls Lead | Define use case, reviewers, capacity, and actions | Accountable for review process | Pilot operating procedure
Risk reviewer | Model Risk Reviewer | Independently review performance, drift, segments, and incidents | May require suspension | Quarterly risk memo
Data owner | Data Engineer | Maintain source mapping, validation, access, and refresh | May stop scoring after quality failure | Data validation report
Decision maker | Project Manager | Accept, override, escalate, or defer score with rationale | Owns project action | Project review record
Executive sponsor | Executive Sponsor | Approve purpose, scope, prohibited uses, and go/no-go | Final pilot accountability | Signed charter
Prohibited uses: autonomous project approval or rejection; contractual entitlement; safety-critical decisions; personnel evaluation; legal conclusions; claims of causality; or scoring outside the approved data and review process.

## Human_Review
Human Review Workflow
The reviewer must evaluate the score with current project context before action.
Step | Stage | Required Review | Owner | Output | Exception
REV-01 | Verify data | Confirm snapshot date, budget, CPI/SPI, progress, workflow metrics, and completeness. | Data Engineer | Data valid | Stop review and correct data
REV-02 | Review probabilities | Evaluate cost, schedule, and overall probabilities—not only risk band. | Project Controls Lead | Risk understood | Escalate uncertainty
REV-03 | Review drivers | Compare feature importance and rule-based triggers with project evidence. | Project Manager | Drivers confirmed or rejected | Document disagreement
REV-04 | Review context | Consider owner decisions, procurement, scope changes, phase, forecasts, and known events. | Project Manager | Context documented | Add missing context
REV-05 | Select decision | Accept, Override, Escalate, or Defer. | Project Manager | Decision recorded | Executive escalation if required
REV-06 | Assign action | Create cost, schedule, workflow, procurement, or coordination action with owner and due date. | Project Controls Lead | Action plan | No action without owner
REV-07 | Close loop | Record outcome, action completion, and later actual results for monitoring. | Data Scientist | Learning record | Include in monitoring history

## Action_Register
Pilot Action Register
Actions must be completed before any real-project production use.
ID | Workstream | Action | Priority | Owner | Start | Due | Evidence | Status | Completion Date | Notes
ACT-001 | Governance | Approve model charter and prohibited uses | Critical | Executive Sponsor | Day 1 | Day 15 | Signed charter | Not Started
ACT-002 | Independent review | Review methodology, leakage boundary, metrics, thresholds, and limitations | Critical | Model Risk Reviewer | Day 1 | Day 20 | Risk review memo | Not Started
ACT-003 | Reproducibility | Re-run complete pipeline in controlled environment | High | Data Scientist | Day 1 | Day 20 | Reproducibility report | Not Started
ACT-004 | Data mapping | Map approved source fields to 40 predictor fields | Critical | Data Engineer | Day 10 | Day 30 | Data mapping spec | Not Started
ACT-005 | Quality gates | Implement automated critical validation before scoring | Critical | Data Engineer | Day 15 | Day 40 | Validation output | Not Started
ACT-006 | Reviewer training | Train project-controls and PM reviewers | High | Project Controls Lead | Day 20 | Day 45 | Training evidence | Not Started
ACT-007 | Silent pilot | Run approved de-identified silent scoring | High | Data Scientist | Day 31 | Day 55 | Silent-pilot report | Not Started
ACT-008 | Threshold review | Evaluate thresholds and review capacity | High | Model Risk Reviewer | Day 45 | Day 60 | Threshold memo | Not Started
ACT-009 | Visible pilot | Conduct limited human-reviewed pilot | Critical | Project Controls Lead | Day 61 | Day 85 | Review log | Not Started
ACT-010 | Monitoring | Evaluate drift, calibration, segment behavior, and overrides | Critical | Model Risk Reviewer | Day 61 | Day 88 | Monitoring report | Not Started
ACT-011 | Incident process | Test model suspension and communication workflow | High | Executive Sponsor | Day 45 | Day 70 | Incident simulation | Not Started
ACT-012 | Go/no-go | Approve continuation, redesign, retraining, or stop | Critical | Executive Sponsor | Day 86 | Day 90 | Decision record | Not Started

## RACI
RACI Matrix
R = Responsible, A = Accountable, C = Consulted, I = Informed.
Activity | Executive Sponsor | Project Controls Lead | Project Manager | Data Engineer | Data Scientist | Model Risk Reviewer
Model charter | A | C | C | I | I | R
Data mapping and quality | I | C | I | R | C | C
Model training and release | I | C | I | C | R | A
Independent model review | I | C | I | C | C | A/R
Human project review | I | A | R | I | C | C
Override approval | I | A/R | R | I | I | C
Monitoring and retraining decision | A | C | I | C | R | R
Model incident suspension | A/R | C | I | C | C | R

## Model_Risk_Register
Model Risk Register
Risks remain open until mitigations and evidence are complete.
Risk ID | Risk | Impact | Likelihood | Rating | Description | Mitigation | Owner | Status | Due
MR-001 | Synthetic-to-real gap | High | High | Critical | Real project distributions may differ from generated data. | Silent pilot, drift analysis, independent validation | Model Risk Reviewer | Open | Before visible pilot
MR-002 | Schedule temporal degradation | High | Medium | High | Schedule ROC-AUC decreased on the future test period. | Monitor, recalibrate, retrain, or redesign schedule model | Data Scientist | Open | Before pilot
MR-003 | Data leakage | High | Low | High | Final or post-outcome fields could enter scoring. | Locked feature manifest and automated schema check | Data Engineer | Open | Each release
MR-004 | Probability miscalibration | Medium | Medium | Medium | Risk probabilities may not match actual rates. | Brier and calibration monitoring | Data Scientist | Open | Monthly
MR-005 | Segment underperformance | High | Medium | High | Performance may vary by project type or delivery environment. | Segment metrics and minimum sample controls | Model Risk Reviewer | Open | Quarterly
MR-006 | Automation bias | High | Medium | High | Reviewers may accept risk bands without context. | Mandatory review form and override option | Project Controls Lead | Open | Pilot
MR-007 | Excessive overrides | Medium | Medium | Medium | High override rate may indicate model or process mismatch. | Override monitoring and reason analysis | Project Controls Lead | Open | Monthly
MR-008 | Stale model | Medium | Medium | Medium | Changing markets or workflows may reduce performance. | Annual review and trigger-based retraining | Data Scientist | Open | Annual
MR-009 | Unauthorized use | High | Low | High | Scores used for prohibited decisions. | Access control, training, audit, incident process | Executive Sponsor | Open | Continuous
MR-010 | Poor data quality | High | Medium | High | Missing or incorrect predictors can distort scores. | Stop-scoring critical quality gate | Data Engineer | Open | Each refresh

## Override_Log
Model Decision and Override Log Template
Each project score requires a recorded decision; overrides require evidence.
Review ID | Project ID | Review Date | Model Version | Cost Prob. | Schedule Prob. | Risk Band | Decision | Override Reason | Reviewer | Action ID | Outcome Follow-Up
1.0.0
1.0.0
1.0.0
1.0.0
1.0.0
1.0.0
1.0.0
1.0.0
1.0.0
1.0.0
1.0.0
1.0.0
1.0.0
1.0.0
1.0.0
1.0.0
1.0.0
1.0.0
1.0.0
1.0.0

## Benefits_Tracking
Pilot Benefits and Learning Tracker
Benefits are not claimed until observed and supported by evidence.
ID | Benefit / Learning | Baseline | 60-Day Actual | 90-Day Actual | Target | Status | Owner | Evidence | Notes
BEN-001 | Review efficiency | Median time from refresh to project review |  |  | ≤3 business days | Not Started | Project Controls Lead | Review timestamps
BEN-002 | Action completion | High-risk project actions completed by due date |  |  | ≥85% | Not Started | Project Manager | Action register
BEN-003 | Earlier detection | Projects identified before final Red controls status |  |  | Measure only | Not Started | Data Scientist | Historical comparison
BEN-004 | Forecast quality | Reduction in unincorporated approved changes |  |  | ≥30% | Not Started | Project Controls Lead | Forecast logs
BEN-005 | Model usefulness | Reviewer usefulness rating |  |  | ≥4 of 5 | Not Started | Model Risk Reviewer | Reviewer survey
BEN-006 | Override learning | Overrides with complete documented reason |  |  | 100% | Not Started | Project Controls Lead | Override log
BEN-007 | Data quality | Critical checks passed before scoring |  |  | 100% | Not Started | Data Engineer | Validation report

## Sources
Sources and Governance References
Project files and professional methodology sources.
Source Type | Source | Location / URL | Use
Project | Model card | documentation/model_card.md | Purpose, use, limits
Project | Model manifest | analysis/models/model_manifest.json | Version, schema, thresholds
Project | Monitoring demo | automation/output/model_monitoring_report.json | Drift and performance
Methodology | IBM CRISP-DM | https://www.ibm.com/docs/en/spss-modeler/18.6.0?topic=dm-crisp-help-overview | Deployment
Methodology | ASQ DMAIC | https://asq.org/quality-resources/dmaic | Improve and Control
Methodology | Microsoft Data Science Lifecycle | https://learn.microsoft.com/en-us/shows/dev-intro-to-data-science/what-is-the-data-science-lifecycle-2-of-28 | Deployment and acceptance
Methodology | PMI Process Groups | https://www.pmi.org/standards/process-groups | Governance